## Sheet1
Final Year Project Portal WBS | [11 empty] | Week - 08-Sep | [6 empty] | Week 14-Sep | [6 empty] | Week 21-Sep | [6 empty] | Week 28-Sep | [6 empty] | Week 05-Oct | [6 empty] | Week 12-Oct | [6 empty] | Week 19-Oct | [6 empty] | Week 26-Oct | [6 empty] | Week 02-Nov | [6 empty] | Week 09-Nov | [6 empty] | Week 16-Nov | [6 empty] | Week 23-Nov | [6 empty] | Week 30-Nov
[12 empty] | September 2025 | [22 empty] | September 2025 | [30 empty] | October 2025 | [29 empty] | November 2025
ID | Predecessors | Phase | Activity Name | Description | Responsibilities | Start Week | End Week | Duration | Plan Start | Plan End | Actual Start | Actual End | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
 | time axis 2025-09-08 to 2025-12-07
Phase 1: Project Initiation
1.1 | - | Initiation | Project Idea Selection | Choose project topic and list its goals | Project Manager | Week 1 | Week 1 | 7 | 2025-09-08 | 2025-09-14 | bar: 2025-09-08 to 2025-09-14
[11 empty] | 2025-09-08 | 2025-09-14 | bar: 2025-09-08 to 2025-09-14
1.2 | 1.1 | Initiation | Project Proposal Preparation | Write a short proposal with scope and objectives | All Members | Week 1 | Week 1 | 7 | 2025-09-08 | 2025-09-14 | bar: 2025-09-08 to 2025-09-14
[11 empty] | 2025-09-08 | 2025-09-14 | bar: 2025-09-08 to 2025-09-14
1.3 | 1.2 | Initiation | Project Charter Development | Make a charter with timeline and team roles | Project Manager | Week 2 | Week 2 | 7 | 2025-09-15 | 2025-09-21 | bar: 2025-09-15 to 2025-09-21
[11 empty] | 2025-09-15 | 2025-09-21 | bar: 2025-09-15 to 2025-09-21
Phase 2: Requirements and Planning
2.1 | 1.3 | Planning | Requirements Gathering | List what the system must do | All Members | Week 2 | Week 2 | 7 | 2025-09-15 | 2025-09-21 | bar: 2025-09-15 to 2025-09-21
[11 empty] | 2025-09-15 | 2025-09-21 | bar: 2025-09-15 to 2025-09-21
2.2 | 2.1 | Planning | System Analysis & Risk Identification | Check requirements and find possible risks | Team Lead | Week 3 | Week 3 | 7 | 2025-09-22 | 2025-09-28 | bar: 2025-09-22 to 2025-09-28
[11 empty] | 2025-09-22 | 2025-09-28 | bar: 2025-09-22 to 2025-09-28
2.3 | 2.1 | Planning | Budget & Resource Planning | Set budget and assign tasks to team members | Project Manager | Week 3 | Week 3 | 7 | 2025-09-22 | 2025-09-28 | bar: 2025-09-22 to 2025-09-28
[11 empty] | 2025-09-22 | 2025-09-28 | bar: 2025-09-22 to 2025-09-28
Phase 3: System Design
3.1 | 2.2, 2.3 | Design | UI/UX Design | Design screens for students, supervisors and committee | UI/UX Designer | Week 4 | Week 4 | 7 | 2025-09-29 | 2025-10-05 | bar: 2025-09-29 to 2025-10-05
[11 empty] | 2025-09-29 | 2025-10-05 | bar: 2025-09-29 to 2025-10-05
3.2 | 2.2, 2.3 | Design | Database & Architecture Design | Plan database tables and system structure | Backend Developer | Week 4 | Week 4 | 7 | 2025-09-29 | 2025-10-05 | bar: 2025-09-29 to 2025-10-05
[11 empty] | 2025-09-29 | 2025-10-05 | bar: 2025-09-29 to 2025-10-05
Phase 4: Development
4.1 | 3.1, 3.2 | Development | Login & Authentication Module | Build login and signup for all users | Frontend Developer | Week 5 | Week 5 | 7 | 2025-10-06 | 2025-10-12 | bar: 2025-10-06 to 2025-10-12
[11 empty] | 2025-10-06 | 2025-10-12 | bar: 2025-10-06 to 2025-10-12
4.2 | 3.1, 3.2 | Development | Supervisor Search Module | Let students search and filter supervisors | Full Stack Developer | Week 5 | Week 6 | 14 | 2025-10-06 | 2025-10-19 | bar: 2025-10-06 to 2025-10-19
[11 empty] | 2025-10-06 | 2025-10-19 | bar: 2025-10-06 to 2025-10-19
4.3 | 4.1 | Development | Proposal Submission & Approval | Allow students to submit proposals online | Full Stack Developer | Week 6 | Week 7 | 14 | 2025-10-13 | 2025-10-26 | bar: 2025-10-13 to 2025-10-26
[11 empty] | 2025-10-13 | 2025-10-26 | bar: 2025-10-13 to 2025-10-26
4.4 | 4.3 | Development | Weekly Progress Reports Module | Students upload reports and get supervisor feedback | Backend Developer | Week 7 | Week 8 | 14 | 2025-10-20 | 2025-11-02 | bar: 2025-10-20 to 2025-11-02
[11 empty] | 2025-10-20 | 2025-11-02 | bar: 2025-10-20 to 2025-11-02
4.5 | 4.2 | Development | Meeting Scheduling Module | Students can book meetings with supervisors | Full Stack Developer | Week 8 | Week 8 | 7 | 2025-10-27 | 2025-11-02 | bar: 2025-10-27 to 2025-11-02
[11 empty] | 2025-10-27 | 2025-11-02 | bar: 2025-10-27 to 2025-11-02
4.6 | 4.4, 4.5 | Development | Deadline Reminder & Notification | Send automatic reminders for deadlines | Backend Developer | Week 8 | Week 9 | 14 | 2025-10-27 | 2025-11-09 | bar: 2025-10-27 to 2025-11-09
[11 empty] | 2025-10-27 | 2025-11-09 | bar: 2025-10-27 to 2025-11-09
4.7 | 4.6 | Development | FYP Committee Dashboard | Committee can manage groups and generate reports | Full Stack Developer | Week 9 | Week 10 | 14 | 2025-11-03 | 2025-11-16 | bar: 2025-11-03 to 2025-11-16
[11 empty] | 2025-11-03 | 2025-11-16 | bar: 2025-11-03 to 2025-11-16
Phase 5: Testing and QA
5.1 | 4.7 | Testing | Unit & Integration Testing | Test each module and check how they work together | QA Engineer | Week 10 | Week 10 | 7 | 2025-11-10 | 2025-11-16 | bar: 2025-11-10 to 2025-11-16
[11 empty] | 2025-11-10 | 2025-11-16 | bar: 2025-11-10 to 2025-11-16
5.2 | 5.1 | Testing | User Acceptance & Security Testing | Test with real users and check for security issues | QA + Project Manager | Week 11 | Week 11 | 7 | 2025-11-17 | 2025-11-23 | bar: 2025-11-17 to 2025-11-23
[11 empty] | 2025-11-17 | 2025-11-23 | bar: 2025-11-17 to 2025-11-23
Phase 6: Deployment
6.1 | 5.2 | Deployment | Server Setup & Web Deployment | Set up server and launch the portal online | DevOps / Developer | Week 12 | Week 12 | 7 | 2025-11-24 | 2025-11-30 | bar: 2025-11-24 to 2025-11-30
[11 empty] | 2025-11-24 | 2025-11-30 | bar: 2025-11-24 to 2025-11-30
6.2 | 5.2 | Deployment | User Training | Teach users how to use the system | Project Manager | Week 12 | Week 12 | 7 | 2025-11-24 | 2025-11-30 | bar: 2025-11-24 to 2025-11-30
[11 empty] | 2025-11-24 | 2025-11-30 | bar: 2025-11-24 to 2025-11-30
Phase 7: Project Closure
7.1 | 6.1, 6.2 | Closure | Documentation Submission | Collect and submit all project documents | All Members | Week 13 | Week 13 | 7 | 2025-12-01 | 2025-12-07 | bar: 2025-12-01 to 2025-12-07
[11 empty] | 2025-12-01 | 2025-12-07 | bar: 2025-12-01 to 2025-12-07
7.2 | 7.1 | Closure | Final Project Review & Sign-off | Do final meeting and get approval | Project Manager | Week 13 | Week 13 | 7 | 2025-12-01 | 2025-12-07 | bar: 2025-12-01 to 2025-12-07
[11 empty] | 2025-12-01 | 2025-12-07 | bar: 2025-12-01 to 2025-12-07