## Sheet1
Resource Sheet |  |  |  |  | Resource Assigned
Resource Name | Type | Std Rate | Role | Max Unit | Task/ Resource Name | Assigned Resources
Project Manager | work | 5,000/hr | Management | 100% | Project Idea Selection | Project Manager
Team Lead | work | 3,500/hr | Management | 100% | Project Proposal Preparation | Project Manager, Team Lead
UI/UX Designer | work | 2,000/hr | Design | 100% | Project Charter Development | Project Manager
Backend Developer | work | 1,000/hr | Developer | 100% | Requirements Gathering | Project Manager, Team Lead
Frontend Developer | work | 2,000/hr | Developer | 100% | System Analysis & Risk Identification | Team Lead
FullStack Developer | work | 500/hr | Developer | 100% | Budget & Resource Planning | Project Manager
Server | Cost | Fixed Cost: $5000
QA Engineer | work | 800/hr | Testing | 100% | UI/UX Design | UI/UX Designer
[5 empty] | DB & Architecture Design | Backend Developer
[5 empty] | Login & Authentication Module | Frontend Developer
[5 empty] | Supervisor Search Module | FullStack Developer
Working Hours |  |  |  |  | Proposal Submission & Approval | FullStack Developer
[5 empty] | Weekly Progress Reports Module | Backend Developer
Task | Est. Duration | Working Hrs |  |  | Meeting Scheduling Module | FullStack Developer
Project Initiation | 21 | 168 |  |  | Deadline Reminder & Notification | Backend Developer
Requirements and Planning | 14 | 112 |  |  | FYP Committee Dashboard | FullStack Developer
System Design | 7 | 56 |  |  | Unit & Integration Testing | QA Engineer
Development | 77 | 616 |  |  | User Acceptance & Security Testing | Project Manager, QA Engineer
Testing and QA | 14 | 112 |  |  | Server Setup & Web Deployment | FullStack Developer,Server
Deployment | 7 | 56 |  |  | User Training | Project Manager
Project Closure | 14 | 112 |  |  | Documentation Submission | Project Manager, Team Lead
[5 empty] | Final Project Review & Sign-off | Project Manager
Total Working Hours |  | 1232
Resource | Status
FullStack Developer | Overallocated (Resolved)
Issue | Solution
FullStack Developer overallocated: Max Units reduced to 50%, but task assignments (Supervisor Search Module, Proposal Submission & Approval, Meeting Scheduling Module, FYP Committee Dashboard, Server Setup & Web Deployment) were still at 100% Units, exceeding resource capacity. | Reduced assignment Units on all FullStack Developer tasks from 100% to 50% to match resource Max Units, resolving the overallocation (confirmed via Resource Usage/Resource Graph view).