## Task Cost Estimation
Final Year Project Portal — Task Cost Estimation
Note: 1 Day = 8 Standard Hours
Task Name | Days | Standard Hours/Day | Estimated Hours | Rate/Hour (PKR) | Total Cost (PKR)
Project Initiation | 28 | 8 | 224 | 4625 | 1036000
Requirements & Planning | 28 | 8 | 224 | 4250 | 952000
System Design | 14 | 8 | 112 | 1500 | 168000
Development | 84 | 8 | 672 | 791.67 | 532002.24
Testing / Quality Assurance | 21 | 8 | 168 | 2200 | 369600
Deployment | 14 | 8 | 112 | 2794.64 | 312999.68
Project Closure | 21 | 8 | 168 | 4500 | 756000
TOTAL TASK COST |  |  | 1680 |  | 4126601.92

## Resource Cost Estimation
Final Year Project Portal — Resource Cost Estimation
Resource Name | Days Worked | Hours/Day | Total Hours Worked | Rate/Hr (PKR) | Total Pay (PKR)
Project Manager | 63 | 8 | 504 | 5000 | 2520000
Team Lead | 28 | 8 | 224 | 3500 | 784000
UI/UX Designer | 7 | 8 | 56 | 2000 | 112000
Backend Developer | 35 | 8 | 280 | 1000 | 280000
Frontend Developer | 7 | 8 | 56 | 2000 | 112000
FullStack Developer | 56 | 8 | 448 | 500 | 224000
QA Engineer | 14 | 8 | 112 | 800 | 89600
Server (Hosting – Fixed Cost) | - | - | - | - | 5000
TOTAL RESOURCE COST |  |  |  |  | 4126600

## Budget Summary
Final Year Project Portal — Project Budget Summary
Grand Total (Task Cost): | 4126601.92
Grand Total (Resource Cost): | 4126600
Approved Budget: | 2800000
Status: | Over Budget
Task | Total Cost (PKR) | Resource | Total Pay (PKR)
Project Initiation | 1036000 | Project Manager | 2520000
Requirements & Planning | 952000 | Team Lead | 784000
System Design | 168000 | UI/UX Designer | 112000
Development | 532002.24 | Backend Developer | 280000
Testing / Quality Assurance | 369600 | Frontend Developer | 112000
Deployment | 312999.68 | FullStack Developer | 224000
Project Closure | 756000 | QA Engineer | 89600
|  | Server (Hosting – Fixed Cost) | 5000